## Bug Tracker
Bug ID | Date Reported | Reported By | Contact Info | Bug Description | Steps to Reproduce | Environment / Configuration | Attachments (Links) | Severity | Priority | Status | Assigned To | Date Assigned | Resolution Notes | Date Resolved
BUG-001 | 2026-04-10 | Sarah Chen | s.chen@company.com | Login page crashes on Safari 17 when autofill is enabled | 1. Open Safari 17 2. Navigate to /login 3. Enable autofill 4. Enter credentials 5. Click Sign In | Safari 17.3, macOS Sonoma 14.4, Production | https://drive.company.com/screenshots/bug001 | Critical | P1 | In Progress | Dev - Marcus Lee | 2026-04-11
BUG-002 | 2026-04-12 | James Patel | j.patel@company.com | Export to CSV drops rows when dataset exceeds 10,000 records | 1. Create or load a dataset with >10,000 rows 2. Click Export > CSV 3. Open the downloaded file 4. Compare row counts | Chrome 124, Windows 11, Staging | https://drive.company.com/screenshots/bug002 | High | P2 | Open | Dev - Yuki Tanaka | 2026-04-13
BUG-003 | 2026-04-15 | Rachel Moore | r.moore@company.com | Dark mode toggle resets to light mode after browser refresh | 1. Log in to the app 2. Enable dark mode via settings 3. Refresh the browser 4. Observe theme reverts to light | Firefox 125, Ubuntu 22.04, Production |  | Low | P3 | Open | Dev - Aisha Okonkwo | 2026-04-16
BUG-004 | 2026-04-17 | Tom Nguyen | t.nguyen@company.com | Dashboard chart fails to load when date range spans across years | 1. Go to Dashboard 2. Set date range from Dec 2025 – Jan 2026 3. Observe chart area shows spinner indefinitely | Chrome 124, macOS, Production | https://drive.company.com/screenshots/bug004 | High | P1 | Resolved | Dev - Marcus Lee | 2026-04-18 | Fixed timezone boundary issue in date query builder. Deployed in v3.2.1. | 2026-04-25
BUG-005 | 2026-04-20 | Linda Park | l.park@company.com | Password reset email not delivered when username contains uppercase letters | 1. Create account with uppercase in username (e.g. 'JohnDoe') 2. Log out 3. Click Forgot Password 4. Enter email 5. Check inbox — no email received | All browsers, Production |  | High | P2 | In Progress | Dev - Yuki Tanaka | 2026-04-21
BUG-006 | 2026-04-28 | Carlos Rivera | c.rivera@company.com | Tooltip text overflows container on mobile screens (< 375px width) | 1. Open app on iPhone SE or any device < 375px wide 2. Hover or long-press any chart data point 3. Tooltip text extends beyond screen edge | Safari/Chrome, iOS 17, iPhone SE, Production | https://drive.company.com/screenshots/bug006 | Low | P3 | Open